## Sheet1
SEVERITY
| Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level |  |  | Minimal | Minor | Moderate | Major | Severe
1 | Not able to complete all task assigned | Need to complete tasks in time so that all tasks get completed | I will ensure that I finish the tasks in time and invest extra time if needed | Follow the plan | 3 | 12 | 12 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | My files gets deleted | If files get deleted or lost | Make sure to have saved a copy on a USB stick and on Github | Have a backup for the project | 6 | 9 | 9 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | My desktop computer breaks | Make sure desktop computer does not break | Have an alternative laptop to carry on the project | Have an alternative computer in hand | 6 | 5 | 5 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Wanting to change something at last minute | If I need to change something on my project | Have a plan which is well thought in advance and stick to it | Create a structured plan which will avoid last minute changes | 4 | 6 | 6 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | My internet stops working | If internet suddenly stops working | I will ensure that my hotspot will work and in case it breaks I will ask the internet provider to fix it | Make sure I have a stable internet connection at all times | 9 | 10 | 10 |  | Unlikely | 1 | 2 | 3 | 4 | 5
6 | Security Risk | Someone hacks into my java code and change it | I will need to keep my files on a computer which is password protected | Find the best way to protect my code | 6 | 10 | 10
7 | Software not working | If Eclipse stops working | Find an alternative software which can replace Eclipse | Haven alternative softwares in case software breaks | 5 | 8 | 8
8 | Application has bugs | The application will present bugs when it is run | I will ensure that tests are done and any bugs are resolved | Test the application | 8 | 12 | 12